PROJECT DELIVERY RECORD | REVIEW EDITION, OCTOBER 2026

# TRIMLY

Web booking and service operations platform | Ibadan, Nigeria

From manual operations to a public launch

Precious Olusayo | Project Manager
Delivery period: 6 October 2025 - 25 June 2026

| PUBLIC LAUNCH | TEAM | SCHEDULE | BUDGET |
| --- | --- | --- | --- |
| 26 May 2026 | 8 people | 21 days after baseline | Within approved budget |

## Project mandate and delivered scope

Deliver a web booking service with Paystack payments and manual / WhatsApp barber coordination for Ibadan. The approved MVP excluded a mobile app. The project combined software delivery with operational readiness, launch and handover. [A, C]

## Delivery ownership

Precious led planning, prioritization and delivery control across the cross-functional team. The supplied record attributes sprint planning and reviews, scope protection, risk tracking, the launch-delay recommendation, readiness confirmation and closure communication to Precious. [A, C, D]

## Recorded operational outcomes

The first three months recorded 210 completed bookings. The account also reports 50 active barbers, 99% uptime, 97% payment success, 76% booking completion and a 24% 30-day repeat rate. The measure-specific reporting windows are retained in the outcomes register. [E]

Purpose of this package A structured record of the project timeline, selected Jira issues, delivery decisions, launch events and reported outcomes for professional review.

Basis: compiled from project information supplied and confirmed by Precious Olusayo. The issue register and approval summaries are transcribed from that account, not a native Jira export or original signed approval records. References [A-F] identify sections of the supplied account. All budget amounts and spend breakdowns are withheld.

01 / TIMELINE VIEW

# Delivery across nine calendar months

Actual dates and spans supplied in the project account, plotted from October 2025 through June 2026. Point events mark the month in which they occurred. [A]

| Milestone / activity | Oct 2025 | Nov 2025 | Dec 2025 | Jan 2026 | Feb 2026 | Mar 2026 | Apr 2026 | May 2026 | Jun 2026 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project initiation & requirements gathering | = |  |  |  |  |  |  |  |  |
| MVP scope definition & approval | o |  |  |  |  |  |  |  |  |
| Design milestone: web booking flow |  | o |  |  |  |  |  |  |  |
| Development start |  | o |  |  |  |  |  |  |  |
| Sprint cycles (18 reported) |  | = | = | = | = | = | = | = |  |
| Core booking system complete |  |  |  |  |  | o |  |  |  |
| Paystack integration complete |  |  |  |  |  | o |  |  |  |
| Barber onboarding process live |  |  |  |  |  |  | o |  |  |
| Soft launch: internal, friends & family |  |  |  |  |  |  | o |  |  |
| Planned public launch: original baseline |  |  |  |  |  |  |  |  |  |
| Actual public launch |  |  |  |  |  |  |  | o |  |
| Post-launch stabilization |  |  |  |  |  |  |  | = | = |
| Project closure & handover |  |  |  |  |  |  |  |  | o |

Legend: o = dated milestone; = = explicit activity span. Blank cells mean no date/span supplied for that month, not an assertion that no work occurred. The original baseline row has no actual event.

Launch baseline and variance Original public-launch target: 5 May 2026. Reported public launch: 26 May 2026. Difference: 21 calendar days, equal to three weeks.

The source describes a nine-month project. The dated delivery record runs from 6 October 2025 to 25 June 2026, across the nine named months October-June. This chart does not invent a phase-by-phase daily schedule.

02 / MILESTONE REGISTER

# Baseline versus actual delivery

Original planned and actual dates are preserved. Ownership labels mirror the supplied account. [A]

| Milestone | Original plan | Actual date / span | Owner |
| --- | --- | --- | --- |
| Project initiation & requirements gathering | 6 Oct 2025 | 6-15 Oct 2025 | Precious Olusayo |
| MVP scope definition & approval | 22 Oct 2025 | 24 Oct 2025 | Precious + Founders |
| Design milestone: web booking flow | 15 Nov 2025 | 18 Nov 2025 | Product Designer |
| Development start | 20 Nov 2025 | 20 Nov 2025 | Lead Developer |
| Sprint cycles (18 reported) | Continuous | 20 Nov 2025 - 15 May 2026 | Precious (facilitator) |
| Core booking system complete | 28 Feb 2026 | 12 Mar 2026 | Lead Developer |
| Paystack integration complete | 15 Mar 2026 | 28 Mar 2026 | Developer 2 |
| Barber onboarding process live | 5 Apr 2026 | 10 Apr 2026 | Operations |
| Soft launch: internal, friends & family | 20 Apr 2026 | 25 Apr 2026 | Precious |
| Planned public launch: original baseline | 5 May 2026 | - | Not supplied |
| Actual public launch | 5 May 2026 | 26 May 2026 | Precious + Founders |
| Post-launch stabilization | 26 May 2026 - 15 Jun 2026 | 26 May 2026 - 20 Jun 2026 | Precious |
| Project closure & handover | 20 Jun 2026 | 25 Jun 2026 | Precious |

Referenced supporting material includes kickoff notes, MVP approval, Figma comments, a feature-completion ticket, payment testing logs, onboarding checklist v1.2, soft-launch report, go-live authorization, hypercare log and closure email. The historical source files are referenced by the supplied account; they are not attached here.

Reported sprint activity: 20 November 2025 - 15 May 2026; 18 sprints. Eighteen biweekly reports are also reported. Individual sprint dates and report dates have not been supplied, so no synthetic sprint calendar is included. [A, C]

03 / SELECTED ISSUE REGISTER

# TRIM project | Delivery records

Eight supplied issue records. All are reported Done; approximately 87 total project tickets are referenced in the account. Dates are creation and resolution dates, not a timestamped audit history. [B]

| Issue | Summary / classification | Assignee | Created | Resolved |
| --- | --- | --- | --- | --- |
| TRIM-12 | Create web booking form - location, service, time Story ¦ Booking Core ¦ Sprint 2 ¦ High | Dev 1 | 22 Nov 2025 | 8 Dec 2025 |
| TRIM-19 | Integrate Paystack payment gateway Story ¦ Payments ¦ Multiple ¦ Highest | Dev 2 | 5 Dec 2025 | 28 Mar 2026 |
| TRIM-27 | Build simple barber allocation logic Story ¦ Operations ¦ Sprint 7 ¦ High | Dev 1 | 18 Dec 2025 | 15 Feb 2026 |
| TRIM-41 | WhatsApp notification templates for job assignment Task ¦ Operations ¦ Sprint 9 ¦ Medium | Ops Lead | 12 Jan 2026 | 3 Mar 2026 |
| TRIM-58 | Fix booking confirmation email not sending Bug ¦ Booking Core ¦ Soft Launch ¦ Highest | Dev 2 | 22 Apr 2026 | 24 Apr 2026 |
| TRIM-63 | Payment retry logic for failed transactions Story ¦ Payments ¦ Pre-Launch ¦ Highest | Dev 2 | 28 Apr 2026 | 18 May 2026 |
| TRIM-71 | Soft-launch feedback - improve error messages Task ¦ UX ¦ Pre-Launch ¦ High | Designer | 27 Apr 2026 | 12 May 2026 |
| TRIM-79 | Go-live checklist completion Task ¦ Launch ¦ Launch ¦ Highest | Precious | 20 May 2026 | 26 May 2026 |

Reporter on all eight supplied records: Precious. Source issue keys, role labels, sprint labels and priorities are retained. No missing descriptions, estimates or status-change dates have been created.

## TRIM-19 | Reported transition sequence

Paystack payment gateway To Do > In Progress > Code Review > Testing > Blocked (edge cases) > In Progress > Done

The source supplies this ordered sequence only. Individual transition timestamps, actors and time-in-status values are not supplied. The companion workbook retains the sequence as seven entries.

04 / CLOSURE BOARD

# Trimly Launch Board

Compiled status view of the eight supplied issue records at the referenced 25 June 2026 project snapshot. [B, F]

| TO DO ¦ 0 | IN PROGRESS ¦ 0 | TESTING ¦ 0 | DONE ¦ 8 |
| --- | --- | --- | --- |
| No supplied issues in this status at closure. | No supplied issues in this status at closure. | No supplied issues in this status at closure. | TRIM-12 ¦ Story Create web booking form - location, service, time Dev 1 ¦ High TRIM-19 ¦ Story Integrate Paystack payment gateway Dev 2 ¦ Highest TRIM-27 ¦ Story Build simple barber allocation logic Dev 1 ¦ High TRIM-41 ¦ Task WhatsApp notification templates for job assignment Ops Lead ¦ Medium TRIM-58 ¦ Bug Fix booking confirmation email not sending Dev 2 ¦ Highest TRIM-63 ¦ Story Payment retry logic for failed transactions Dev 2 ¦ Highest TRIM-71 ¦ Task Soft-launch feedback - improve error messages Designer ¦ High TRIM-79 ¦ Task Go-live checklist completion Precious ¦ Highest |

This board summarizes the supplied records; it does not represent a captured Jira interface or the full project backlog. The remaining approximately 79 issue records are not included, and their final statuses are not inferred.

05 / DELIVERY GOVERNANCE

# Scope, risk and schedule decisions

Selected decisions and risk topics attributed to Precious in the supplied project account. Budget amounts are withheld. [A, C]

| Date | Recorded decision | Authority / rationale |
| --- | --- | --- |
| 11 Feb 2026 | Request to add an iOS app rejected for the current phase. | Precious; protect budget and timeline. |
| 18 May 2026 | Three-week public-launch delay recommended and approved. | Precious recommended; founders approved. Unresolved payment retry issues cited. |
| 22 May 2026 | All critical launch criteria confirmed met at final go/no-go review. | Precious; readiness decision. |

## Risk topics tracked

| Risk | Related recorded action / detail |
| --- | --- |
| Payment failures during peak hours | Payment testing / retry work and the 18 May launch-delay decision. |
| Barber no-shows | Listed in the risk register; response details not supplied. |
| Scope creep from founders | 11 February decision to exclude an iOS app from the phase. |
| Technical debt from rapid build | Listed in the risk register; response details not supplied. |

Risk register last updated: 15 May 2026. Ratings, probability scores and individual mitigation owners are not supplied.

## Reported contributors to the launch delay

Payment edge-case testing: 12 days. WhatsApp job-allocation iterations: 8 days. A critical booking-flow bug discovered during soft launch: 4 days. [A]

The launch variance is 21 calendar days. The listed work durations total 24 days but cannot be mapped to that variance without overlap / critical-path details. They are retained separately, not summed as a delay model. The reported 18 May approval occurred after the original 5 May target; no earlier approval is invented.

06 / LAUNCH DOCUMENTATION

# Readiness, authorization and handover

Launch-related events are reported below in chronological order. The checklist and approval descriptions summarize the account; no original signatures or approval emails are reproduced. [C, D]

PUBLIC LAUNCH ¦ 26 MAY 2026 Approval reported from both founders following Precious's recommendation. Individual founder names were not supplied. Project-manager readiness sign-off is dated 25 May 2026.

| Date / period | Event / record | Reported outcome | Owner / approver |
| --- | --- | --- | --- |
| 25 Apr 2026 | Soft Launch Report | Internal + friends-and-family soft launch | Precious |
| 20 May 2026 | UAT Summary | 14 critical/high bugs fixed; 3 medium bugs deferred | Not supplied |
| 22 May 2026 | Final go/no-go decision | All critical launch criteria confirmed met | Precious |
| 25 May 2026 | Launch Readiness Checklist | Completed and signed off, as reported | Precious |
| 26 May 2026 | Go-Live Authorization | Both founders approved after Precious's recommendation | Both founders |
| 26 May 2026 - 20 Jun 2026 | Hypercare Log | Daily monitoring by Precious | Precious |
| 25 Jun 2026 | Project Closure Email | Closure email to founders; lessons learned attached, as reported | Precious |

## UAT disposition | 20 May 2026

| Critical / high bugs | Medium bugs |
| --- | --- |
| 14 fixed | 3 deferred |

The supplied UAT summary does not name all 17 defects or provide the detailed acceptance checklist. No additional test results, waiver approvals or signatories have been inserted. The source references daily hypercare monitoring and a closure email with lessons learned; their original content is not included.

07 / OUTCOME REGISTER

# Delivery and operating results

Reported values confirmed by the project manager. The account references monitoring, payment and operating records, but the underlying data exports are not part of this package. [E]

| Measure | Result | Reporting window | Referenced source |
| --- | --- | --- | --- |
| Project duration | 9 months | October 2025 - June 2026 | Timeline: 6 Oct 2025 - 25 Jun 2026 |
| Cross-functional team | 8 | Project delivery period | Team roster in kick-off notes |
| Budget performance | Within approved budget | Project closure | Final budget tracker |
| Launch variance | 3 weeks | 5 May to 26 May 2026 | Decision log and launch dates |
| Uptime | 99% | First 90 days after launch | Post-launch monitoring dashboard |
| Payment success | 97% | Reporting period not specified separately | Paystack export and internal reconciliation |
| Booking completion | 76% | 26 May - 25 Aug 2026 | Booking system analytics |
| Active barbers | 50 | Reporting date not specified separately | Operations barber roster |
| Completed bookings | 210 | First three months after launch | Booking system export |
| 30-day repeat rate | 24% | Post-launch report | Cohort analysis |

## Measurement boundaries

Uptime is reported for the first 90 days. Booking completion is explicitly dated 26 May - 25 August 2026. Completed bookings use the first-three-months period. These windows are not silently equated. Payment success and the active-barber count have no separately specified period in the supplied account.

Metric definitions, event denominators and individual transaction / customer records are not supplied. No monthly trend, customer list, synthetic export or budget-derived calculation has been added.

08 / REFERENCED RECORDS

# Artifact index and compilation basis

The following original artifacts are named in the supplied project account. This index is a reference inventory, not a claim that the files below are attached or independently authenticated. [F]

| Referenced artifact | Original date / period | Owner | Relevance |
| --- | --- | --- | --- |
| Project Kick-off Notes | 6 Oct 2025 | Precious | Initiation |
| MVP Scope & Approval | 24 Oct 2025 | Precious + Founders | Scope baseline |
| Risk Register v4 | 15 May 2026 | Precious | Risk management |
| Decision Log | Continuous | Precious | Governance |
| Jira Export (TRIM project) | Snapshot: 25 Jun 2026 | System | Development history |
| Soft Launch Report | 25 Apr 2026 | Precious | Testing evidence |
| Launch Readiness Checklist | 25 May 2026 | Precious | Go-live decision |
| Go-Live Authorization | 26 May 2026 | Founders | Formal approval |
| Post-Launch Metrics Dashboard | 25 Aug 2026 | Precious | Outcomes |
| Project Closure & Lessons Learned | 25 Jun 2026 | Precious | Handover |

## Source and confidentiality

Source: Pasted markdown(3).md, project information supplied and confirmed by Precious Olusayo. Section references: A timeline; B Jira issue records; C delivery documentation; D launch and approvals; E outcomes; F artifact index. Confidential budget amounts and actual expenditure are omitted from all deliverables.

## Record alignment notes

Sprint reporting: 18 sprints and 18 biweekly reports are retained as reported; no dated sprint calendar is inferred. The development window is shorter than 18 uninterrupted two-week intervals.

Bug identity: TRIM-58 was resolved on 24 April, before the reported 25 April soft launch. It is not treated as the unnamed critical booking-flow bug said to have been discovered during soft launch.

Approval provenance: historical approval events are transcribed from the project manager's account. This document is a current compilation, not a newly created historical signature, email or Jira audit trail.